## Look-ahead
YOUR LOGO
Your Company Name |  |  | 3-WEEK LOOK-AHEAD
Street address · City, State ZIP |  |  |  |  | Pale yellow cells are yours to fill in | [20 empty] | WEEK OF | 2026-10-05
Phone · Email · License no. |  |  |  |  | All other cells are locked | [20 empty] | REVISION
JOB
PROJECT | [9 empty] | Example: the Week of date is an example; type the day your look-ahead starts
SUPERINTENDENT
[5 empty] | Week 1 · 10/5 | [6 empty] | Week 2 · 10/12 | [6 empty] | Week 3 · 10/19
[5 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S
ACTIVITY | RESPONSIBLE | START | FINISH | DAYS | 2026-10-05 | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19 | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | STATUS | CONSTRAINTS
Example: frame second floor walls | Framing crew | 2026-10-05 | 2026-10-09 | 5 | [21 empty] | On track | bar: Week 1 · 10/5 M to Week 1 · 10/5 F
Example: set roof trusses | Framing crew | 2026-10-12 | 2026-10-14 | 3 | [21 empty] | Not started | Example: truss delivery confirmed | bar: Week 2 · 10/12 M to Week 2 · 10/12 W
Example: plumbing rough-in | Plumber | 2026-10-14 | 2026-10-21 | 8 | [21 empty] | Not started | bar: Week 2 · 10/12 W to Week 3 · 10/19 W
Bars fill from the dates you type. Weekend days show so weekend work can be planned; leave them out of an activity's dates when no one works.
Free template from Framing & Figures · framingandfigures.com/templates/

## About this template
ABOUT THIS TEMPLATE
What the file does, how to use it and where to learn more
3-Week Look-Ahead Schedule Template (Excel)
Up to twenty-five activities with a responsible party, start and finish dates, and bars that fill across twenty-one days from the week you set, with the days of each activity counted, a status and the constraints to clear first.
HOW TO USE IT
STEP 1 | Fill in the letterhead: your company name, address, and the phone, email and license line. Then type the week of date, the first day of the three weeks, which sets every day column: the date shown is only an example, so replace it with your own. Then the revision, the project and the superintendent. To remove the YOUR LOGO text, choose Review > Unprotect Sheet (there is no password), then protect the sheet again.
STEP 2 | Add one activity per line, up to 25: the activity, who is responsible, the start and finish dates, the status (Not started, On track, Behind or Done) and the constraints, what must happen first. Days and the bars compute themselves: days counts the start through the finish, reads Check dates when a finish comes before its start, and the bar fills each day in between. Bars fill from the dates you type. Weekend days show so weekend work can be planned; leave them out of an activity's dates when no one works.
STEP 3 | Read the weekday letters and the dates across the top, under the Week 1, Week 2 and Week 3 bands that show each week's first date. When you reissue the look-ahead, update the week of date and the revision, then print it: it fits one landscape page.
EXAMPLE FIGURES | The first three lines are the example, with the week of set to October 5, 2026: framing the second floor walls runs 5 days, setting the roof trusses 3 days and the plumbing rough-in 8 days, so the days read 5, 3 and 8 and the bars fill 5, 3 and 8 cells. The day columns run from 10/5 to 10/25. Replace them, and the week of date, with your own.
VERSION | v2, 2026-09-24
LICENSE | © Harmony For Humanity LLC. Free for use in your business; not for resale.
LINKS
TEMPLATE PAGE | 3-Week Look-Ahead Schedule Template (Excel)
ALL TEMPLATES | framingandfigures.com/templates/
RELATED TEMPLATES | Construction Schedule Template (Excel)
Construction Daily Report Template (Excel)
Construction Meeting Minutes Template (Word)
Punch List Template (Excel)