## Budget
CONSTRUCTION BUDGET
Budget, commitments, actuals and projected cost by cost code
PROJECT |  |  |  |  | Pale yellow cells are yours to fill in
JOB NO. |  |  |  |  | All other cells are locked
DATE
PREPARED BY
SUMMARY
Original budget |  |  | 95000 | The Budget column added up
Approved change orders (added cost) |  |  | 2500 | Example: replace with your signed change orders
Current budget |  |  | 97500 | Original budget plus approved change orders
Committed |  |  | 66800 | Purchase orders and subcontracts, the Committed column added up
Actual to date |  |  | 56500 | Costs booked so far, the Actual to date column added up
Estimate to complete |  |  | 39500 | What is left to spend, the Estimate to complete column added up
Projected final |  |  | 96000 | Actual to date plus estimate to complete, line by line
Variance |  |  | 1500 | Current budget less projected final; below zero is an overrun
% spent |  |  | 58.85% | Actual to date as a share of the projected final cost
COST CODES
COST CODE | DESCRIPTION | COST TYPE | BUDGET | COMMITTED | ACTUAL TO DATE | ESTIMATE TO COMPLETE | PROJECTED FINAL | VARIANCE | % SPENT
01 00 00 | Example: general conditions | Other | 12000 | 0 | 4500 | 7500 | 12000 | 0 | 37.5%
03 30 00 | Example: concrete | Subcontractors | 28000 | 28000 | 14000 | 14000 | 28000 | 0 | 50%
06 10 00 | Example: framing lumber | Materials | 22000 | 23800 | 23800 | 0 | 23800 | -1800 | 100%
06 10 00 | Example: framing labor | Labor | 18000 | 0 | 9200 | 8000 | 17200 | 800 | 53.49%
22 00 00 | Example: plumbing | Subcontractors | 15000 | 15000 | 5000 | 10000 | 15000 | 0 | 33.33%
TOTALS BY COST TYPE
COST TYPE |  |  | BUDGET | COMMITTED | ACTUAL TO DATE |  | PROJECTED FINAL
Materials |  |  | 22000 | 23800 | 23800 |  | 23800
Labor |  |  | 18000 | 0 | 9200 |  | 17200
Subcontractors |  |  | 43000 | 43000 | 19000 |  | 43000
Equipment |  |  | 0 | 0 | 0 |  | 0
Other |  |  | 12000 | 0 | 4500 |  | 12000
Total |  |  | 95000 | 66800 | 56500 |  | 96000
Lines not counted above |  |  | 0 | 0 | 0 |  | 0
Free template from Framing & Figures · framingandfigures.com/templates/

## About this template
ABOUT THIS TEMPLATE
What the file does, how to use it and where to learn more
Construction Budget Template (Excel)
Budget, committed cost, actual cost to date and estimate to complete by cost code roll up to a projected final cost, the variance and percent spent, with totals by cost type, approved change orders added to the current budget, and overruns highlighted.
HOW TO USE IT
STEP 1 | Fill in the project block. Then enter the budget from your estimate, one line per cost code: its code, a description, its cost type and the budget amount.
STEP 2 | As purchase orders, subcontracts and invoices are booked, enter each line's committed cost and its actual cost to date. Enter a credit or a back charge as a negative amount.
STEP 3 | Each month, type each line's estimate to complete, then read its projected final cost and variance: a variance below zero is an overrun, and it is shaded. Approved change orders go on the summary, where they raise the current budget.
EXAMPLE FIGURES | The five example lines and the $2,500.00 of approved change orders are illustrative figures, not recommendations or typical costs. The framing lumber line runs $1,800.00 over its budget, so you can see an overrun shaded. Replace them with your own.
VERSION | v2, 2026-09-24
LICENSE | © Harmony For Humanity LLC. Free for use in your business; not for resale.
LINKS
TEMPLATE PAGE | Construction Budget Template (Excel)
CALCULATOR | Bid price calculator
GUIDE | How to build a construction estimate
ALL TEMPLATES | framingandfigures.com/templates/
RELATED TEMPLATES | Construction Estimate Template (Excel)
Change Order Form (Word)
Pay Application Template (Excel)
Labor Burden Spreadsheet (Excel)