## Cash flow
CASH FLOW PROJECTION
Billings, retainage and costs month by month, with the cash position they leave
PROJECT | [7 empty] | Pale yellow cells are yours to fill in
CONTRACT SUM |  |  | 480000 | Example: your contract sum |  |  |  | All other cells are locked
ESTIMATED COST |  |  | 408000 | Example: your estimate of the job cost
RETAINAGE HELD (%) |  |  | 10% | Example: use your own figure
MONTHS FROM BILLING TO PAYMENT |  |  | 1 | Example: 1 is paid a month after billing; use your own figure
RETAINAGE RELEASED IN MONTH |  |  | 10 | Example: use your own month
MONTH BY MONTH
MONTH | WORK THIS MONTH | WORK TO DATE | BILLED | RETAINAGE HELD | NET BILLED | CASH IN | COSTS PAID | NET CASH | CASH POSITION
1 | 5% | 5% | 24000 | 2400 | 21600 | 0 | 20400 | -20400 | -20400
2 | 10% | 15% | 48000 | 4800 | 43200 | 21600 | 40800 | -19200 | -39600
3 | 15% | 30% | 72000 | 7200 | 64800 | 43200 | 61200 | -18000 | -57600
4 | 20% | 50% | 96000 | 9600 | 86400 | 64800 | 81600 | -16800 | -74400
5 | 20% | 70% | 96000 | 9600 | 86400 | 86400 | 81600 | 4800 | -69600
6 | 15% | 85% | 72000 | 7200 | 64800 | 86400 | 61200 | 25200 | -44400
7 | 10% | 95% | 48000 | 4800 | 43200 | 64800 | 40800 | 24000 | -20400
8 | 5% | 100% | 24000 | 2400 | 21600 | 43200 | 20400 | 22800 | 2400
9 |  | 100% | 0 | 0 | 0 | 21600 | 0 | 21600 | 24000
10 |  | 100% | 0 | 0 | 0 | 48000 | 0 | 48000 | 72000
11 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 72000
12 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 72000
13 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 72000
14 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 72000
15 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 72000
16 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 72000
17 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 72000
18 |  | 100% | 0 | 0 | 0 | 0 | 0 | 0 | 72000
Totals |  |  | 480000 | 48000 | 432000 | 480000 | 408000 | 72000
Work entered: 100%
LOWEST POINT
Lowest cash position |  |  | -74400
Month of the lowest position |  |  | 4
Example: your planned percent complete for each month
Costs are taken as paid in the month the work is done.
Billing is figured on work done, with retainage held from each bill and paid back in the month you choose.
A blank work percent counts as 0.
Free template from Framing & Figures · framingandfigures.com/templates/

## About this template
ABOUT THIS TEMPLATE
What the file does, how to use it and where to learn more
Construction Cash Flow Projection Template (Excel)
Your planned percent complete for each of eighteen months gives the S-curve, the amount billed, the retainage held and the cash that comes in after the lag you set. Against the costs paid, it shows the cash position month by month and the lowest point.
HOW TO USE IT
STEP 1 | Type the project, the contract sum, the estimated cost, the retainage held as a percent of each bill, the months from billing to payment (0 to 3) and the retainage released in month (1 to 18). The figures shown are only an example, so replace them with your own.
STEP 2 | Type your planned percent complete for each month in the work this month column. A blank month counts as 0. Work to date adds them up as the S-curve, and the line under the column shows the work entered in all.
STEP 3 | Read the cash position column month by month, then the lowest cash position and the month it falls in. Billed, retainage held, net billed, cash in, costs paid and net cash are arithmetic on the figures you typed, shown in whole dollars.
EXAMPLE FIGURES | A $480,000.00 contract with an estimated cost of $408,000.00, 10% retainage, one month from billing to payment, retainage released in month 10, and work of 5, 10, 15, 20, 20, 15, 10 and 5 percent in months 1 to 8. The cash position is lowest at -$74,400.00 in month 4. Replace them with your own.
METHOD | Cash in for a month is the net billed of the month you set earlier, plus, in the release month only, the retainage held in all 18 months. Retainage released is the total held over all months, paid in the month you choose. Costs paid are the estimated cost times the work percent, in the month of the work. A bill paid after month 18 does not show as cash in.
VERSION | v2, 2026-09-24
LICENSE | © Harmony For Humanity LLC. Free for use in your business; not for resale.
LINKS
TEMPLATE PAGE | Construction Cash Flow Projection Template (Excel)
CALCULATOR | Retainage calculator
GUIDE | Retainage in construction
ALL TEMPLATES | framingandfigures.com/templates/
RELATED TEMPLATES | Pay Application Template (Excel)
Construction Budget Template (Excel)
Construction Schedule Template (Excel)
WIP Schedule Template (Excel)