## Closeout
CLOSEOUT CHECKLIST
Every closeout item, who is responsible and where it stands
| Pale yellow cells are yours to fill in | PROJECT
| All other cells are locked | JOB NO. |  | SUBSTANTIAL COMPLETION
OWNER
NO. | ITEM | RESPONSIBLE | DUE | DATE DONE | STATUS | NOTES
PUNCH LIST AND INSPECTIONS
1 | Punch list walked with the owner | Superintendent |  | 2026-09-28 | Done
2 | Punch list items completed and verified |  |  |  | In progress | Example: two doors still need hardware
3 | Final inspections passed
4 | Occupancy certificate or final approval received
DOCUMENTS FOR THE OWNER
5 | As-built drawings delivered
6 | Operation and maintenance manuals delivered
7 | Warranties collected and delivered
8 | Attic stock and spare parts delivered
9 | Keys, codes and access cards turned over
SYSTEMS AND TRAINING
10 | Equipment started up and tested
11 | Owner's staff trained on systems
12 | Training attendance recorded
FINANCIAL
13 | Final change orders signed
14 | Final pay application submitted
15 | Retainage release requested
16 | Lien waivers collected from subs and suppliers
17 | Consent of surety obtained, on bonded jobs
18 | Subcontracts and purchase orders closed
SITE
19 | Temporary utilities and facilities removed
20 | Final cleaning done
21 | Site restored and debris removed
22 | Signs, fences and trailers removed
PROJECT RECORDS
23 | Job files and photos archived
24 | Lessons learned noted
25 | Closeout meeting held with the owner
OTHER ITEMS
26
27
28
29
SUMMARY
Not started |  | 0
In progress |  | 1
Done |  | 1
N/A |  | 0
Done, of items with a status (N/A left out) |  | 50%
Free template from Framing & Figures · framingandfigures.com/templates/

## About this template
ABOUT THIS TEMPLATE
What the file does, how to use it and where to learn more
Construction Closeout Checklist (Excel)
Closeout items in six sections, from the punch list to the project records, each with who is responsible, a due date, the date done and a status, with four blank lines for your own items, counts by status and the share of items done.
HOW TO USE IT
STEP 1 | Fill in the project, the job no., the owner and the substantial completion date. Then, for each item, fill in Responsible, Due and Date done: who does it, when it is due and when it was done.
STEP 2 | Choose its Status (Not started, In progress, Done or N/A) and add a note in Notes where it helps. Add your own items on the blank lines at the end. To change a printed item, choose Review > Unprotect Sheet (there is no password), edit it, then protect the sheet again.
STEP 3 | Read the summary: the count of items at each status, and the share done, which is Done out of the items that have a status, N/A items left out. An item with no status yet is not counted.
EXAMPLE | Item 1 is marked Done, with Superintendent responsible and 9/28/2026 as the date done, and item 2 In progress with the note "Example: two doors still need hardware". The summary then reads Not started 0, In progress 1, Done 1 and N/A 0, with 50.00% done. Clear them before you use the sheet; every other field starts blank.
METHOD | The items are prompts, not a complete list and not a statement of what your contract or the law requires. Add your own on the blank lines.
VERSION | v2, 2026-09-24
LICENSE | © Harmony For Humanity LLC. Free for use in your business; not for resale.
LINKS
TEMPLATE PAGE | Construction Closeout Checklist (Excel)
CALCULATOR | Retainage calculator
GUIDE | Retainage in construction
ALL TEMPLATES | framingandfigures.com/templates/
RELATED TEMPLATES | Punch List Template (Excel)
Construction Quality Control Checklist (Excel)
Pay Application Template (Excel)
Submittal Log Template (Excel)