## Checklist
YOUR LOGO
Your Company Name |  | QC CHECKLIST
Street address · City, State ZIP |  |  | INSPECTION NO.
Phone · Email · License no. |  |  | DATE
Pale yellow cells are yours to fill in
All other cells are locked
INSPECTION
PROJECT
AREA OR PHASE INSPECTED
TRADE OR SUBCONTRACTOR
INSPECTED BY
NO. | ITEM | RESULT | NOTES
BEFORE WORK STARTS
1 | Drawings and specs on site are current | Pass
2 | Submittals approved for this work
3 | Materials on site match approved submittals | Fail | Example: window model differs from the approved submittal
4 | Layout and dimensions checked
5 | Preceding work ready for this trade
SITEWORK AND FOUNDATIONS
6 | Subgrade prepared and inspected
7 | Forms, reinforcing and embeds checked
8 | Anchor bolts and sleeves where drawn
9 | Concrete tickets checked at delivery
FRAMING AND STRUCTURE
10 | Members, sizes and spacing match drawings
11 | Connectors and fasteners installed
12 | Sheathing nailing checked
13 | Openings sized and headers in place
MECHANICAL, ELECTRICAL AND PLUMBING ROUGH-IN
14 | Rough-in locations match drawings
15 | Penetrations sealed or firestopped
16 | Pressure or continuity tests done
17 | Rough-in inspections passed before cover
BUILDING ENVELOPE
18 | Window and door flashing installed
19 | Water-resistive barrier lapped and taped
20 | Roofing and roof flashing complete
21 | Sealant joints complete
INTERIOR FINISHES
22 | Drywall finish checked under a work light
23 | Paint coverage and color checked
24 | Flooring flat, clean and undamaged
25 | Doors, hardware and trim adjusted
FINAL
26 | Fixtures and equipment working
27 | Labels and tags in place
28 | Area cleaned
29 | Punch list items entered
OTHER ITEMS
30
31
32
33
SUMMARY
Pass |  | 1
Fail |  | 1
N/A |  | 0
DEFICIENCIES
ITEM NO. | DEFICIENCY AND ACTION | RESPONSIBLE | DUE | DATE CORRECTED
3 | Example: window model differs from submittal; confirm with the architect or replace | Superintendent | 2026-10-02
SIGN-OFF
INSPECTED BY
DATE
ACCEPTED BY
DATE
Free template from Framing & Figures · framingandfigures.com/templates/

## About this template
ABOUT THIS TEMPLATE
What the file does, how to use it and where to learn more
Construction Quality Control Checklist (Excel)
A printable inspection checklist of 29 prompts in seven sections, from before work starts to final, each answered Pass, Fail or N/A, with counts of each answer, four blank lines for your own items, a deficiencies table, and sign-off lines for the inspector and whoever accepts the work.
HOW TO USE IT
STEP 1 | Fill in your company, the inspection no. and date, then the project, the area or phase inspected, the trade or subcontractor and who inspected it. Go through the work with the sheet and mark each item Pass, Fail or N/A, with a note where it helps; add your own items on the blank lines at the end. To remove the YOUR LOGO text, choose Review > Unprotect Sheet (there is no password), then protect the sheet again.
STEP 2 | List each item that failed under Deficiencies: its item no., the deficiency and action, who is responsible, when it is due, and the date corrected once it is fixed.
STEP 3 | Sign it under Inspected by and date it, have whoever accepts the work sign under Accepted by and date it, and keep it with the job's quality records. To change a printed item, choose Review > Unprotect Sheet (there is no password), edit it, then protect the sheet again.
EXAMPLE | Item 1 is marked Pass, and item 3 Fail with the note "Example: window model differs from the approved submittal" and one deficiency for it: "Example: window model differs from submittal; confirm with the architect or replace", Superintendent, due 10/2/2026. Clear them before you use the sheet; every other field starts blank.
METHOD | The items are prompts, not a complete list and not a statement of what any code or specification requires. The project's drawings and specifications govern. Add your own on the blank lines.
VERSION | v2, 2026-09-24
LICENSE | © Harmony For Humanity LLC. Free for use in your business; not for resale.
LINKS
TEMPLATE PAGE | Construction Quality Control Checklist (Excel)
ALL TEMPLATES | framingandfigures.com/templates/
RELATED TEMPLATES | Punch List Template (Excel)
Construction Closeout Checklist (Excel)
Submittal Log Template (Excel)
Construction Daily Report Template (Excel)