## Schedule
CONSTRUCTION SCHEDULE
Tasks, workdays and weekly Gantt bars
PROJECT | [7 empty] | Pale yellow cells are yours to fill in
PROJECT START |  | 2026-09-14 | Example: type your own start date |  |  |  |  | All other cells are locked
PROJECT FINISH |  | 2026-11-05 | The latest end date below |  |  |  |  | Scheduled work
UPDATED | [7 empty] | Done (100% complete)
[7 empty] | ◆ | Milestone (0 workdays)
WEEK STARTING
NO. | TASK | RESPONSIBLE | START | DURATION (WORKDAYS) | END | % COMPLETE | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19 | 2026-10-26 | 2026-11-02 | 2026-11-09 | 2026-11-16 | 2026-11-23 | 2026-11-30 | 2026-12-07 | 2026-12-14 | 2026-12-21 | 2026-12-28
1 | Example: site prep | Your crew | 2026-09-14 | 3 | 2026-09-16 | 100%
2 | Example: foundation | Concrete sub | 2026-09-17 | 5 | 2026-09-23 | 100%
3 | Example: framing | Framing crew | 2026-09-24 | 10 | 2026-10-07 | 10%
4 | Example: rough-ins | MEP subs | 2026-10-08 | 8 | 2026-10-19 | 0%
5 | Example: rough-in inspection | Inspector | 2026-10-20 | 0 | 2026-10-20 | 0% | bar: 2026-10-19
6 | Example: drywall and finish | Drywall sub | 2026-10-21 | 12 | 2026-11-05 | 0%
End dates skip Saturdays and Sundays but not holidays. A task of 0 workdays is a milestone, marked ◆.
Free template from Framing & Figures · framingandfigures.com/templates/

## About this template
ABOUT THIS TEMPLATE
What the file does, how to use it and where to learn more
Construction Schedule Template (Excel)
Tasks with a start, duration and end date, percent complete, milestones and conditional-formatting Gantt bars across the weeks of the job.
HOW TO USE IT
STEP 1 | Type your project and its start date, then one task per row: who is responsible, when it starts and how many workdays it takes (0 for a milestone).
STEP 2 | End dates and the weekly bars fill in by themselves, skipping Saturdays and Sundays but not holidays. Each example task starts the workday after the one above it ends; type a date over any start to set your own.
STEP 3 | Update % complete as the work gets done: a task at 100% turns hi-vis yellow. Print the sheet to share the plan.
EXAMPLE FIGURES | The project start and the six tasks labeled Example show how the dates and bars work. Their dates, durations and % complete are placeholders, not typical times for the work. Replace them with your own.
VERSION | v2, 2026-09-24
LICENSE | © Harmony For Humanity LLC. Free for use in your business; not for resale.
LINKS
TEMPLATE PAGE | Construction Schedule Template (Excel)
ALL TEMPLATES | framingandfigures.com/templates/
RELATED TEMPLATES | Construction Estimate Template (Excel)
Construction Daily Report Template (Excel)
Punch List Template (Excel)
Pay Application Template (Excel)