## Submittal log
SUBMITTAL LOG
Submittals sent for review, response dates and days in review
PROJECT
JOB NO.
Pale yellow cells are yours to fill in
All other cells are locked
SUBMITTAL NO. | SPEC SECTION | DESCRIPTION | SUBCONTRACTOR OR SUPPLIER | REQUIRED ON SITE | RECEIVED FROM SUB | SENT FOR REVIEW | RETURNED | DAYS IN REVIEW | STATUS | NOTES
1 | 03 20 00 | Example: rebar shop drawings | Example: concrete sub | 2026-09-20 | 2026-09-05 | 2026-09-06 | 2026-09-13 | 7 | Approved
2 | 08 50 00 | Example: window schedule | Example: window supplier | 2026-10-10 | 2026-09-18 | 2026-09-19 |  |  | Submitted
STATUS SUMMARY
[9 empty] | Pending | 0
[9 empty] | Submitted | 1
[9 empty] | Approved | 1
[9 empty] | Approved as noted | 0
[9 empty] | Revise and resubmit | 0
[9 empty] | Rejected | 0
Free template from Framing & Figures · framingandfigures.com/templates/

## About this template
ABOUT THIS TEMPLATE
What the file does, how to use it and where to learn more
Submittal Log Template (Excel)
Each submittal with its spec section, supplier and the dates it is required on site, received, sent for review and returned, the days it spent in review and its status, with counts by status.
HOW TO USE IT
STEP 1 | Log each submittal as you send it: its number, spec section, description, subcontractor or supplier, and when it is required on site.
STEP 2 | Enter the dates received from the sub, sent for review and returned as they happen; days in review and the status counts fill in by themselves.
STEP 3 | Pick a status as each submittal moves through review, and check the status counts to see what is still outstanding.
EXAMPLE FIGURES | The first two rows are the example: one submittal returned Approved in 7 days and one still out for review. Replace them with your own.
VERSION | v2, 2026-09-24
LICENSE | © Harmony For Humanity LLC. Free for use in your business; not for resale.
LINKS
TEMPLATE PAGE | Submittal Log Template (Excel)
ALL TEMPLATES | framingandfigures.com/templates/
RELATED TEMPLATES | RFI Form (Word)
RFI Log Template (Excel)
Construction Meeting Minutes Template (Word)
Change Order Form (Word)